## Progress Report 2
Work Log
Item | Date | Start | Finish | Time | Notes
Video Response | 2024-01-23 | 22:00 | 23:00 | 1:00
Software Development Document | 2024-01-24 | 21:00 | 23:00 | 2:00
Call Flow Diagram | 2024-01-25 | 21:00 | 23:00 | 2:00
Peer Feedback | 2024-01-27 | 21:00 | 22:00 | 1:00
Component Diagram | 2024-01-28 | 15:00 | 17:00 | 2:00
TAXII Client Build | 2024-01-28 | 17:00 | 22:00 | 5:00
TAXII Server Research | 2024-01-28 | 22:00 | 23:00 | 1:00
Wireframe Diagrams in Figma | 2024-02-01 | 21:00 | 23:00 | 2:00
Wireframe Diagrams in Figma | 2024-02-02 | 21:00 | 23:00 | 2:00
Requirments Matrix | 2024-02-03 | 17:00 | 18:30 | 1:30
GUI Development | 2024-02-03 | 18:30 | 19:30 | 1:00
research technologies to build app with | 2024-02-03 | 19:30 | 21:30 | 2:00
Frontend Development | 2024-02-03 | 21:30 | 24:00 | 0.10417
Frontend Development | 2024-02-04 | 8:00 | 11:00 | 3:00
Progress Report | 2024-02-04 | 11:00 | 12:00 | 1:00
Class Diagram | 2024-02-04 | 12:00 | 15:00 | 3:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
|  |  | Total | 1899-12-31 08:00
Formulas:
Time = SUM(E3:[Time, row above])

## Progress Report 3
Work Log
Item | Date | Start | Finish | Time | Notes
Technology Research - Conducted research on best technologies and frameworks to use for frontend web development for UI. Landed on Flask with a possible React frontend | 2024-02-05 | 20:00 | 23:30 | 3:30
Dev Session: Using Dash by python to implement frontend visuals and UI | 2024-02-09 | 19:00 | 23:00 | 4:00
Dev Session: Using react to implement UI. Completed initial setup using pure react and Flask. Dash was too opinionated for my given use case. | 2024-02-10 | 17:00 | 20:00 | 3:00
Research: Identified backend API requirements for passing information between Flask and React. Heavy compliation and validation will be done using python in Flask server while React frontend handles all visuals. | 2024-02-11 | 20:00 | 23:00 | 3:00
Research: Identified best visualizer library for building the STIX graphs. Plan to use D3.js. | 2024-02-16 | 20:00 | 23:00 | 3:00
Research: Identified best architecture for taxii proxy to fit in the current client server TAXII data flow for testing and demoing. I plan to create two different TAXII clients that require different STIX schemas to test conversion functionality. I also plan to use one custom TAXII server for sending custom designed STIX objects as well as a OSINT TAXII server for testing solution on intelligence in the wild. | 2023-02-17 | 20:00 | 23:00 | 3:00
Dev Session: Using react to implement frontend UI. Changed list component to a table component for better functionality | 2024-02-18 | 8:00 | 12:00 | 4:00
Dev Session: Worked on Implementing Visualizer page for TAXII Proxy | 2024-02-18 | 13:00 | 17:30 | 4:30
Dev Session: Worked on Implementing Visualizer page for TAXII Proxy | 2024-02-25 | 15:00 |  | -0.625
0:00
0:00
0:00
0:00
0:00
0
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
|  |  | Total | 0.54167
Formulas:
Time = SUM(E3:[Time, row above])

## Progress 5
Work Log
Item | Date | Start | Finish | Time | Notes
Visualizer: Developing STIX bundle parsing into network graph nodes and links | 2024-03-06 | 21:00 | 23:20 | 2:20
Visualizer: Improve node information displayed | 2024-03-07 | 21:50 | 23:00 | 1:10
Visualizer: Improve node information displayed | 2024-03-09 | 20:00 | 24:00 | 4:00
Research: Looked into more advanced D3.js functionality | 2024-03-10 | 21:00 | 24:00 | 3:00
Research: Looked into more advanced D3.js functionality | 2024-03-11 | 20:00 | 23:00 | 3:00
Visualizer: Added titles to each node | 2024-03-13 | 20:00 | 23:00 | 3:00
Visualizer: Visual Formatting for json view and graph | 2024-03-15 | 21:00 | 23:30 | 2:30
Visualizer: Created Labels for Links | 2024-03-16 | 21:00 | 23:30 | 2:30
Research: Schema Development. How to use schemas to exchange STIX standard enhancements. | 2024-03-17 | 12:00 | 18:00 | 6:00
0:00
0:00
0:00
0:00
0:00
0
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
|  |  | Total | 1899-12-31 03:30
Formulas:
Time = SUM(E3:[Time, row above])

## Report 6
Work Log
Item | Date | Start | Finish | Time | Notes
Research: Schema Development | 2024-03-19 | 22:30 | 24:00 | 1:30
Dev: Added the ability to select a schema based on a list that is pulled from the API backend | 2023-03-23 | 16:00 | 20:00 | 4:00
Dev: Add STIX 2.1 Validation | 2023-03-24 | 10:30 | 14:00 | 3:30
Dev: Add STIX 2.1 Validation | 2023-03-25 | 21:24 | 23:00 | 1:36
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
|  |  | Total | 0.44167
Formulas:
Time = SUM(E3:[Time, row above])